## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Jericha Tolopa | 2024-09-02 | 2024-09-05 | 3 | 100%
1.1.1 | Project Charter Revisions | Jericha Tolopa | 2022-03-15 |  | -44635 | 100%
1.2 | Research | Kathryna Turi | 2022-03-15 | 2022-03-21 | 6 | 90%
1.3 | Projections | Isaac Jacob | 2022-03-16 | 2022-03-22 | 6 | 40%
1.4 | Stakeholders | Virginia Whemby | 2022-03-17 | 2022-03-22 | 5 | 70%
1.5 | Guidelines | Isaac Jacob | 2022-03-18 | 2022-03-22 | 4 | 60%
1.6 | Project Initiation | Jericha Tolopa | 2022-03-23 | 2022-03-23 | 0 | 50%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Kathryna Turi | 2022-03-24 | 2022-03-28 | 4 | 5%
2.2 | Budget | Virginia Whemby | 2022-03-29 | 2022-04-02 | 4 | 30%
2.3 | Communication Plan | Virginia Whemby |  |  | 0 | 0%
2.4 | Risk Management | Kathryna Turi |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Kathryna Turi |  |  | 0 | 0%
3.2 | KPIs | Isaac Jacob |  |  | 0 | 0%
3.2.1 | Monitoring | Jericha Tolopa |  |  | 0 | 0%
3.2.2 | Forecasts | Virginia Whemby |  |  | 0 | 0%
3.3 | Project Updates | Kathryna Turi |  |  | 0 | 0%
3.3.1 | Chart Updates | Jericha Tolopa |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Isaac Jacob |  |  | 0 | 0%
4.2 | Quality Deliverables | Kathryna Turi |  |  | 0 | 0%
4.3 | Effort & Cost Tracking | Virginia Whemby |  |  | 0 | 0%
4.4 | Project Performance | Jericha Tolopa |  |  | 0 | 0%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.